ECOSTEL

Project Scope of Work

Track B — Full-Fledged Marketplace Platform

| Prepared by | Bhavana Kannan |
| --- | --- |
| Prepared for | Soman — Ecostel |
| Project start | May 19, 2026 |
| Project end | August 13, 2026 (12 weeks) |
| Document version | 1.0 |
| Total fee | TBD — see Section 6 |

This document defines the full scope of work, deliverables, milestone dates, acceptance criteria, payment structure, and change-control process for the Ecostel marketplace platform. Both parties should review, agree, and sign before work begins. Any work outside this document requires a written change order.

# 1. Project Summary

Ecostel is a manufacturing marketplace connecting buyers (engineering and procurement teams) with vetted vendors (manufacturers). This engagement covers the full design and development of the platform from brand and UX through to a working, deployed marketplace that real buyers and vendors can use.

The project runs for exactly 12 weeks, from May 19 to August 13, 2025, structured as two phases:

- Phase 1 — Foundation (Weeks 1–5, May 19 – June 21): design system, backend scaffolding, accounts, file uploads, vendor registration, buyer RFQ submission.

- Phase 2 — Core Marketplace (Weeks 6–12, June 22 – August 13): vendor dashboards, quote submission, admin routing, buyer quote comparison, PO acceptance, messaging and notifications.

The engagement is scoped for one developer working across the 12-week period. Any additional engineering resources required to meet deadlines are the responsibility of the client unless agreed otherwise in writing.

# 2. Scope of Work

## 2.1 In Scope

| Deliverable | Description | Phase |
| --- | --- | --- |
| UX/UI Design | User flows, wireframes, high-fidelity screens for all three surfaces (marketing site, buyer workspace, vendor workspace, admin panel). Brand system and component library. | Phase 1 |
| Backend API | NestJS (TypeScript). REST + GraphQL. Auth module (JWT, refresh tokens, RBAC). Full Postgres schema and migrations. | Phase 1 |
| File Upload System | S3 storage, chunked upload (tus protocol), virus scanning (ClamAV), signed URL access. | Phase 1 |
| User Accounts | Sign-up, sign-in, email verification, password reset, 2FA (TOTP), session management. Buyer and vendor org types with RBAC. | Phase 1 |
| Vendor Registration System | Self-serve /for-vendors registration flow. Business documents, capabilities, certifications. Pending state, admin approval, OpenSearch indexing. | Phase 1 |
| Buyer RFQ System | RFQ submission form with multi-part CAD file upload. Draft and submit states. Buyer dashboard listing all RFQs. Admin inbox view. | Phase 1 |
| Vendor Dashboards | Vendor workspace: incoming RFQ queue, RFQ detail view, active orders, profile and capability management. | Phase 2 |
| Vendor Quote Submission | Quote form per RFQ: unit price, lead time, MOQ. Draft and submit states. Quote status machine. | Phase 2 |
| Admin Panel — RFQ Routing | RFQ triage queue, capability-tag vendor recommendations, manual assignment UI, reassignment. | Phase 2 |
| Buyer Quote Comparison UI | Side-by-side quote comparison: price, lead time, MOQ, vendor score, certifications. Recommended badge. | Phase 2 |
| PO Acceptance | Quote acceptance flow, auto-generated PO, order status transitions (production → shipped → delivered), vendor milestone updates. | Phase 2 |
| Messaging & Notifications | Threaded messaging on RFQs and orders, scoped by participant. Email notifications via Postmark for key events. | Phase 2 |
| Deployment & DevOps | Docker containers, AWS ECS Fargate (API), Vercel (frontends), GitHub Actions CI/CD, staging + production environments. | Both |
| Marketing Site | Public ecostel.co: home, capabilities, industries, for-vendors, about, contact. SEO-optimized. Static-first, no auth. | Phase 1 |

## 2.2 Explicitly Out of Scope

The following are NOT included in this engagement. They require a separate written agreement and additional budget before work can begin.

- Live payment processing and escrow (Razorpay / Stripe Connect integration). Payments handled off-platform during the pilot.

- CAD viewer integration (Autodesk Forge or equivalent). File download only during this engagement.

- Advanced ML-based vendor matching (OpenSearch ranking). Basic capability-tag matching only.

- Mobile apps (iOS or Android).

- CMS integration (Sanity or equivalent) for blog or case studies.

- Third-party logistics or carrier API integrations for automated tracking.

- Custom reporting or BI dashboards beyond the admin health panel.

- Content creation: copywriting, photography, or video production.

- Ongoing maintenance or support after August 13, 2026.

# 3. Milestone Schedule & Acceptance Criteria

All milestones are hard dates. If a milestone is missed by more than 3 business days for reasons within the developer's control, the client may request a revised schedule in writing. If missed due to delayed client feedback or approvals, the timeline shifts accordingly (see Section 5).

| Milestone | Due date | Deliverable(s) | Measurable acceptance criteria |
| --- | --- | --- | --- |
| M1 | May 30, 2025 (Week 2) | Design system + wireframes | • All primary buyer, vendor, and admin flows wireframed. • Brand system documented: hex values, Rubik typography, component specs. • Accepted by client in writing within 2 business days of delivery. |
| M2 | June 7, 2025 (Week 3) | Backend scaffolding + auth | • NestJS API running in staging. Auth endpoints return valid JWT. • Buyer and vendor org creation with RBAC tested via Postman. • GitHub Actions CI pipeline green on main branch. |
| M3 | June 14, 2025 (Week 4) | File upload + accounts | • 100 MB CAD file uploaded, scanned clean, retrievable via signed URL. • End-to-end: buyer signs up, verifies email, enables 2FA, signs back in. • End-to-end: vendor signs up, reaches registration wizard. |
| M4 (Phase 1 complete) | June 21, 2025 (Week 5) | Vendor registration + Buyer RFQ | • Vendor registers, uploads docs, admin approves, vendor status = active. • Buyer submits RFQ with CAD upload → RFQ appears in admin inbox. • Marketing site live at staging URL: Lighthouse Performance ≥ 90, SEO = 100, A11y ≥ 95. • Zero unresolved Sentry errors in staging for 48 consecutive hours. |
| M5 | July 5, 2025 (Week 7) | Vendor workspace + quote submission | • Vendor logs in, sees assigned RFQ, submits quote with price / lead time / MOQ. • Quote visible to admin in routing panel. • Admin assigns RFQ to vendor → vendor receives email notification within 2 minutes. |
| M6 | July 19, 2025 (Week 9) | Quote comparison + PO acceptance | • Buyer sees ≥ 2 quotes in side-by-side comparison view. • Buyer accepts quote → PO generated with PO number → vendor sees new order. • Order status machine: production → shipped → delivered transitions working. |
| M7 (Phase 2 complete) | August 6, 2025 (Week 12, buffer) | Messaging + notifications + end-to-end pilot | • Buyer and vendor can message in a thread tied to an RFQ or order. • Email notifications arrive for: RFQ assigned, quote received, PO issued, message sent. • End-to-end pilot: 1 real buyer submits RFQ → admin routes → vendor quotes → buyer accepts → vendor marks shipped. Completed without manual developer intervention. • API error rate < 1% measured in Sentry over 72 hours. • Median time from RFQ submission to first vendor quote < 24 hours (pilot pool). |
| M8 (Final handover) | August 13, 2025 | Production deployment + documentation handover | • Platform live at app.ecostel.co and ecostel.co (production, not staging). • Architecture doc, build plan, and user guide delivered. • All environment variables, secrets, and AWS credentials transferred to client. • Codebase pushed to client-owned GitHub repository. • 30-minute handover call completed. |

# 4. Quantitative Success Metrics

The project is considered successfully completed when ALL of the following are measurably true at handover (August 13, 2025):

| Metric | Target | How measured |
| --- | --- | --- |
| Lighthouse Performance | ≥ 90 on all public pages | Lighthouse CI in GitHub Actions |
| Lighthouse SEO | = 100 on all public pages | Lighthouse CI |
| Lighthouse Accessibility | ≥ 95 on all public pages | Lighthouse CI |
| API error rate (production) | < 1% over 72 hours | Sentry error rate dashboard |
| File upload — max file size | 256 MB upload completes | Manual test + test suite |
| End-to-end marketplace loop | 1 real RFQ → quote → PO without dev intervention | Recorded pilot session |
| Notification delivery time | < 2 minutes from trigger | Timed manual test |
| Staging uptime (Phase 1 exit) | Zero Sentry errors over 48 hrs | Sentry + CloudWatch |
| Code coverage — backend | ≥ 60% unit test coverage | Jest coverage report in CI |
| Documentation delivered | Architecture doc, build plan, user guide, requirements contract | Files transferred to client |
| Codebase handover | Client owns GitHub repo with full history | Repo transfer confirmed |

# 5. Responsibilities & Dependencies

## 5.1 Developer responsibilities

- Design, develop, test, and deploy all in-scope deliverables by the milestone dates in Section 3.

- Provide weekly progress updates every Monday (written summary or short video).

- Flag blockers within 24 hours of identifying them — do not wait until a milestone is at risk.

- Maintain a staging environment accessible to the client at all times after M2.

- Use the agreed tech stack (Next.js, NestJS, PostgreSQL, Redis, AWS S3, ECS Fargate, Vercel).

- Store all code in version control (GitHub) with meaningful commit messages.

## 5.2 Client responsibilities

- Provide written feedback on each milestone within 2 business days of delivery. Silence past 2 business days is treated as approval.

- Make design or content decisions within 1 business day when asked. Delays here shift all subsequent milestone dates by the same number of days.

- Provide access to: AWS account (or fund creation), domain DNS, existing brand assets, and any third-party API credentials needed (Postmark, Razorpay, etc.) all for current system (if applicable). Create accounts if they do not exist for current system.

- Recruit at least 3 pilot vendors and 2 pilot buyers before July 19 (M6) so the end-to-end pilot (M7) can be completed.

- Attend a 30-minute sync call at the completion of each phase (after M4 and after M8).

# 6. Cost & Payment Schedule

This section covers all costs associated with the project. There are two distinct categories: the developer fee (what you pay the developer for their time and work) and software costs (what Ecostel pays to third-party services to run the platform). These are billed separately and to different parties.

## 6.1 Current State — What Ecostel Pays Today

Ecostel's current website is a simple, static marketing site. It displays information but has no logins, no user accounts, no file uploads, and no back-end system. Because of this, the current software costs are minimal and likely limited to a website hosting subscription and a domain name registration.

This project replaces that simple site with a full marketplace platform. As a result, new software services will be introduced during the build. These are listed in Section 6.2 below. Any current hosting or website subscription Ecostel is paying can be cancelled once the new platform goes live, as it will no longer be needed.

Note: the exact cost of the current website setup is not known at the time of writing. Ecostel should confirm this with whoever manages the current site before signing.

## 6.2 Developer Fee

This is the compensation paid to the developer for designing and building the platform over the 12-week engagement. The amount is proposed by the developer and must be agreed by both parties before this document is signed. Payments are split across milestones so that each payment is tied to completed, verified work.

| Payment | Due date | What triggers it | Amount |
| --- | --- | --- | --- |
| Deposit — project kickoff | May 18, 2025 | Both parties sign this document | TBD |
| Phase 1 completion | June 21, 2025 | Client signs off on M4 deliverables | TBD |
| Phase 2 completion | August 6, 2025 | Client signs off on M7 deliverables | TBD |
| Final handover | August 13, 2025 | Code, docs, and accounts transferred | TBD |
| TOTAL DEVELOPER FEE |  |  | TBD |

Amounts to be proposed by the developer and agreed before signing. Until filled in, this section is not binding.

## 6.3 New Software & Infrastructure Costs (paid by Ecostel directly)

Because this project builds a marketplace platform from scratch, one that handles user accounts, file uploads, vendor quotes, orders, and emails, it requires several software services that Ecostel does not currently use. services. Think of these like utilities: just as a physical office needs electricity, internet, and a phone line to operate, a software platform needs hosting, storage, and communication

These costs are paid by Ecostel directly to each service provider. They are not included in the developer fee. The table below explains each one in plain English, shows when it becomes necessary, and gives a realistic cost estimate.

| Service | What it is and why it is needed | Est. cost | When needed |
| --- | --- | --- | --- |
| PHASE 1 — needed from the start of the build (Weeks 1–5) |  |  |  |
| Code storage (GitHub) | Where all the code written for this project is stored and tracked. Every change the developer makes is saved with a history — nothing is ever lost, and the full project can be handed over to Ecostel cleanly at the end. | Free | Week 1 |
| Website delivery (Vercel) | The service that makes the Ecostel website and app load quickly for anyone who visits, anywhere in the world. When a buyer or vendor opens the platform in their browser, this is what delivers the page to them. Free during development; a small monthly fee applies when the platform goes live with personalized domain. | Free during build; ~$20/mo at launch | Week 1 (free tier) |
| Error monitoring (Sentry) | Automatically detects if something breaks on the platform — for example, if a page crashes or a form stops working — and alerts the developer immediately so it can be fixed before users are affected. | Free | Week 3 |
| Usage analytics (Google Analytics) | Tracks basic information about visitors to the public website, how many people visit, which pages they read, and where they came from. Standard for any business website. | Free | Week 2 |
| PHASE 2 — needed when the marketplace goes live (Weeks 6–12) |  |  |  |
| Platform servers & storage (Amazon Web Services) | This is the most significant new cost. It covers three things: (1) the servers that run the marketplace application — processing logins, RFQs, quotes, and orders around the clock; (2) the database that stores all platform data — user accounts, RFQs, quotes, orders; and (3) secure file storage for all uploads — CAD files, drawings, documents, and inspection reports. Think of it as the rent for the digital building the platform runs inside. The cost scales with usage — low at first, growing as more buyers and vendors join. | ~$80–$200/mo (development) ~$150–$400/mo (live, early stage) | Week 3 (dev setup); full cost at launch |
| Automated email (Postmark) | Sends all automated emails the platform generates on behalf of Ecostel — for example: 'A vendor has submitted a quote for your RFQ,' 'Your order has been shipped,' or 'A new message is waiting for you.' Without this, the platform cannot communicate with buyers or vendors by email. Free for low volumes; small fee beyond that. | Free up to 100 emails/mo; ~$15/mo after | Week 6 (Phase 2 start) |
| User behaviour analytics (PostHog) | Shows how buyers and vendors actually use the platform — which steps they complete, where they stop, what they click most. This helps Ecostel understand what is working and what needs to be improved over time. Free at launch scale. | Free at launch scale | Week 6 |
| FUTURE PHASES — not needed during this 12-week engagement |  |  |  |
| Online payments (Razorpay / Stripe) | Processes payments from buyers to vendors through the platform, including holding funds in escrow until an order is delivered. Not active in this engagement — payments will be handled directly between parties during the pilot. | ~1.5–2% per transaction | Phase 3 (future) |
| CAD file viewer (Autodesk Forge) | Lets buyers and vendors view engineering files directly in the browser without needing specialist software installed on their computer. Not active in this engagement — users will download files instead. | Pay-per-view (~$0.01–$0.05 per file) | Phase 3 (future) |

All cost figures are estimates based on typical usage at this scale. Actual AWS costs depend on the number of users, files uploaded, and RFQs processed. The developer will configure automatic billing alerts so Ecostel is notified if monthly costs approach a pre-agreed limit.

## 6.4 Total Cost Summary

The table below brings both cost categories together for a single view of the total project investment required over the 12-week engagement.

| Cost category | Who pays | Estimated total (12 weeks) |
| --- | --- | --- |
| Current website hosting | Ecostel | Unknown — confirm with current provider |
| Developer fee — Section 6.2 | Ecostel → Developer | TBD — agreed before signing |
| New software & infrastructure — Section 6.3 | Ecostel → each provider | ~$200–$800 total over 12 weeks |
| TOTAL NEW PROJECT COST |  | TBD + ~$200–$800 |

Once the new platform is live, the current website hosting subscription can be cancelled — so that existing cost is replaced, not added to the total.

# 7. Change Control

Any request to add, remove, or materially change a deliverable after this document is signed is a change request. Change requests do not take effect until a written change order is signed by both parties.

## What constitutes a change

- Adding any item from the Out of Scope list in Section 2.2.

- Changing the tech stack from what is specified in this document.

- Requesting additional screens, flows, or integrations not listed in Section 2.1.

- Extending the engagement beyond August 13, 2025.

## What does not constitute a change

- Minor visual adjustments to agreed screens (copy, color, spacing) within a milestone review window.

- Bug fixes for functionality agreed in this document that does not work as specified.

- Performance or accessibility improvements needed to meet the metrics in Section 4.

# 8. Agreement & Signatures

By signing below, both parties confirm they have read and understood this document, agree to its terms, and commit to fulfilling their respective responsibilities.

| Developer | Client — Ecostel |
| --- | --- |
| Name: Bhavana Kannan Signature: __________________________ Date: _______________________________ | Name: Soman Signature: __________________________ Date: _______________________________ |